## BOARD OF TECHNICAL EDUCATION

PORVORIM-GOA

November, 2016 Examinations

Programme: Civil Engg./CT

Subject: Construction Management(CE502)/(5008) [Old/Rev.]

# Time Duration: 3 Hrs.                                               Max. Marks: 75

Instructions: 1) All Questions are compulsory.

2) Figures to the right indicate full marks.

3) Assume suitable additional data if required.

| Q.No.1. | Answer any five of the following Questions: | 5 x 3 = 15 |
| --- | --- | --- |
| a) | Prevention is better than cure, how will you achieve this goal on construction site. |  |
| b) | Define planning & state its purpose. |  |
| c) | List down any six important laws/acts related to construction industry. |  |
| d) | What are merits & demerits of functional organisation? |  |
| e) | Define i) Event ii) Total float iii) Network diagram. |  |
| f) | How motivation plays a role in management? |  |
| Q.No.2. | Answer any two of the following Questions: | 2 x 6 = 12 |
| a) | What is significance of introducing ISO 9000 series & mention its features & drawbacks. |  |
| b) | Draw a neat sketch of organisation structure of PWD & private organisation. |  |
| c) | Write down agencies associated with construction industries & their function. |  |
| Q.No.3. | Answer the following Questions: |  |
| a) | Construct network diagram for data given in table. Calculate total project duration & mark critical path. Also, calculate total float EST, LST for each activity. | (8) |
| Activity; 1-2; 1-3; 1-4; 2-4; 3-4; 3-5; 4-7; 4-5; 5-6; 4-6; 7-6. Duration (in months); 04; 06; 14; 08; 10; 07; 08; 06; 04; 07; 09. |
| b) | Write note on “Bar chart & its application”. | (4) |
| Q.No.4. | Answer any two of the following Questions: | 2 x 6 = 12 |
| a) | State leadership types & explain any one type in detail. |  |
| b) | Explain updating & network with detail example. |  |
| c) | Write salient features of any three types of contracting firms. |  |
| Q.No.5. | Answer any two of the following Questions: | 2 x 6 = 12 |
| a) | State importance of quality control for construction work. |  |
| b) | List down safety measures to be adopted in case of fabrication & erection. |  |
| c) | Explain inspection & supervision technique for formwork & steel work. |  |
| Q.No.6. | Write short notes on any three: | 3 x 4 = 12 |
| a) | Scientific management |  |
| b) | Site layout & its importance |  |
| c) | Material management |  |
| d) | Employees Provident Fund act |  |
| e) | Occupational hazards in construction industry |  |

***********