## BOARD OF TECHNICAL EDUCATION

PORVORIM-GOA

April, 2012 Examinations

Programme: Civil Engg./CT

Subject: Construction Management(5008)

# Time Duration: 3 Hrs.                                                Max. Marks: 75

Instructions: 1) All Questions are compulsory.

2) Figures to the right indicate full marks.

3) Assume suitable additional data if required.

| Q.No.1. | Answer any five of the following Questions: | 5 x 3 = 15 |
| --- | --- | --- |
| a) | What is critical path? State its importance in network analysis. |  |
| b) | What is line and staff organization? What are its merits? |  |
| c) | What are the safety measures required to be adopted during a demolition work? |  |
| d) | What are the democratic requirements for a leader? |  |
| e) | Human resource is a key resource in efficient execution of civil works. Explain. |  |
| f) | State the principles of management. How it can be applied to civil engineering projects? |  |
| g) | Briefly explain the role of specifications in controlling the quality of construction work. |  |
| Q.No.2. | Answer any two of the following Questions: | 2 x 6 = 12 |
| a) | With neat sketches, briefly explain the organisational structure of construction corporation and private organisation. |  |
| b) | What is functional organisation? What are its merits and demerits? |  |
| c) | Write a brief note on controlling and decision making in construction industry. |  |
| Q.No.3. | Answer the following Questions: |  |
| a) a) | What is PERT? State its advantages over CPM. ### OR What are Bar charts? What are its limitations? Explain different types of floats and their effect on total project duration. | (4) (4) |
| b) | For the data given in table below, construct the network, mark the critical path on it and calculate the total project duration. Also, compute total float, EST and EFT for each activity. Activity; Sequence; Duration in weeks.. K; 1-2; 3. L; 2-3; 4. M; 2-4; 6. N; 3-5; 8. O; 3-7; Dummy. P; 4-5; 4. Q; 5-7; 5. R; 4-6; 9. S; 6-7; 6. T; 6-8; 8. U; 8-9; 7. V; 7-9; 12. W; 9-10; 6. | (8) |
|  |  | …..2/- |
| Q.No.4. | -2- Answer any two of the following Questions: | 2 x 6 = 12 |
| a) | Explain briefly the quality control techniques to be adopted in respect of following works: - Sanitary and water supply works - Masonry work. |  |
| b) | State the important features and drawbacks of ISO-9000 series. |  |
| c) | Explain briefly the sampling techniques used for testing of materials. |  |
| Q.No.5. | Answer any two of the following Questions: | 2 x 6 = 12 |
| a) | Proper material and equipment management is the key for maximization of profits in construction industry. Offer comments. |  |
| b) | What is communication? Briefly explain different types of communications. |  |
| c) | List the different labour laws related to wages & welfare of employees. Briefly explain Employee Provident Fund Act, 1952. |  |
| Q.No.6. | Write short notes on any three of the following: | 3 x 4 = 12 |
| a) | Occupational Hazards in construction industry |  |
| b) | Site layout and its importance in execution of civil works |  |
| c) | Levels and stages of planning |  |
| d) | Organisational structure of PWD |  |
| e) | Statistical Quality control techniques |  |

***********