## BOARD OF TECHNICAL EDUCATION

PORVORIM-GOA

April, 2015 Examinations

Programme: Civil Engg./CT

Subject: Construction Management(5008)

# Time Duration: 3 Hrs.                                           Max. Marks: 75

Instructions: 1) All Questions are compulsory.

2) Figures to the right indicate full marks.

3) Assume suitable additional data if required.

| Q.No.1. | Answer any five of the following Questions: | 5 x 3 = 15 |
| --- | --- | --- |
| a) | Explain any six Harry foyal’s principle of management. |  |
| b) | Write short note on ‘Role of construction in National Development’. |  |
| c) | State the salient features of network analysis. |  |
| d) | Write down importance of safety on construction site. |  |
| e) | What are the various features of ISO-9000 series? |  |
| f) | Briefly explain the necessity and importance of communication. |  |
| g) | Write advantages and disadvantages of partnership firm. |  |
| Q.No.2. | Answer any two of the following Questions: | 2 x 6 = 12 |
| a) | State the two main stages of planning. Explain any one stage in detail. |  |
| b) | Draw a neat sketch of site layout and explain its importance in execution of construction work. |  |
| c) | Draw a neat organizational chart of line organization and mention its merits and demerits. |  |
| Q.No.3. | Answer the following Questions: |  |
| a) | Construct a neat network and find out the critical path of the project, total project duration, EST, EFT and total float. Activity; 1-2; 2-3; 2-4; 3-5; 3-6; 4-5; 4-6; 5-7; 6-7; 7-8. Duration in weeks; 1; 2; 3; 4; 5; 6; 7; 8; 9; 10. | (8) |
| b) | Briefly explain “Updating of Network”. | (4) |
|  | ### OR |  |
| b) | Write salient features of critical path method. | (4) |
| Q.No.4. | Answer any two of the following Questions: | 2 x 6 = 12 |
| a) | What are the safety measures to be adopted while demolishing a structure? |  |
| b) | Mention the techniques of quality control you will adopt in respect of the following works: (i) Brick masonry (ii) Concreting work. |  |
| c) | Write a brief note on “Material Management” . |  |
| Q.No.5. | Answer any two of the following Questions: | 2 x 6 = 12 |
| a) | Define leadership. Distinguish between Authoritarian leadership and Democratic leadership. |  |
| b) | Explain the various types of communication. |  |
| c) | State the objective and provision of any two of the following acts: i) Factories Act, 1948 ii) Minimum wages Act, 1948 iii) Industrial dispute Act, 1947. |  |

………2/-

-2-

| Q.No.6. | Write short note on any three: | 3 x 4 = 12 |
| --- | --- | --- |
| a) | Occupational hazards in construction Industry |  |
| b) | Qualities of an Ideal leader |  |
| c) | Necessity and functions of Management |  |
| d) | General principles of Inspection |  |
| e) | Statistical quality control technique |  |
| f) | Co-ordinating and controlling |  |

***********