## BOARD OF TECHNICAL EDUCATION

PORVORIM-GOA

November, 2014 Examinations

Programme: Civil Engg./CT

Subject: Construction Management(5008)

# Time Duration: 3 Hrs.                                               Max. Marks:  75

Instructions: 1) All Questions are compulsory.

2) Figures to the right indicate full marks.

3) Assume suitable additional data if required.

| Q.No.1. | Answer any five of the following Questions: | 5 x 3 = 15 |
| --- | --- | --- |
| a) | Define Scientific Management. Mention the important functions of management. |  |
| b) | Explain the importance of site layout. |  |
| c) | What is bar chart? Mention its advantages. |  |
| d) | What is function of Organisation? State its merits and demerits. |  |
| e) | State the general principles of Inspection. |  |
| f) | What precautions are to be taken to avoid accidents in construction site? |  |
| g) | Define Motivation and state its importance. |  |
| Q.No.2. | Answer any two of the following Questions: | 2 x 6 = 12 |
| a) | What are the Duties and Responsibilities of an Engineer? |  |
| b) | Draw a neat Organisational chart for Line and Staff Organisation. Mention its merits and demerits. |  |
| c) | Explain the following types of contracting firms & state their merits and demerits: (i) Sole Proprietorship firm (ii) Private Limited Company. |  |
| Q.No.3. | Answer the following Questions: |  |
| a) | State the Salient feature of CPM. | (4) |
|  | ### OR |  |
| a) | Define:- i) Network Diagram ii) Total float iii) Activity iv) Dummy Activity. | (4) |
| b) | Construct a network diagram and calculate the duration of project in years. Also calculate the total float, EST, LST of each activity. Mark the critical path on the network. | (8) |
| Activity; 1-2; 2-3; 2-4; 4-3; 4-6; 4-5; 3-5; 5-7; 6-7; 7-8. Durations In Months; 2; 5; 8; 7; 13; 4; 0; 5; 3; 10. |
| Q.No.4. | Answer any two of the following Questions: | 2 x 6 = 12 |
| a) | What are the common causes of accidents at construction site? How could these accidents be prevented? |  |
| b) | Explain the statistical quality control by standard deviation method. |  |
| c) | State the various supervision techniques for testing materials adopted in construction Industry. Explain any one technique in detail. |  |
| Q.No.5. | Answer any two of the following Questions: | 2 x 6 = 12 |
| a) | State the types of leadership and explain any one in detail. |  |
| b) | State the objectives and provision of any two of the following acts: i) Employee Provident Fund Act-1952 ii) Trade Union Act 1926 iii) Contract Labour Act-1970. |  |
|  |  | ……2/- |
|  | -2- |  |
| c) | What is the importance of human resource in construction Industry? What step will you take as an engineer to improve the output of human resource to the optimum? |  |
| Q.No.6. | Write short notes on any three: | 3 x 4 = 12 |
| a) | Equipment management |  |
| b) | Role of supervisor |  |
| c) | Safety in storage practice of different construction materials |  |
| d) | Principles of organization |  |
| e) | Principles of management |  |

***********